## Sample Schedule Export
Project Name | Task ID | Task Name | Hierarchy Level | Baseline Start | Baseline Finish | Current Start | Current Finish | Predecessors | Status | Row Type | Include in Critical Path?
Sample Lobby Refresh | P1 | Sample Lobby Refresh | 1 | 2026-01-05 | 2026-01-28 | 2026-01-05 | 2026-01-29 |  | In Progress | Summary
Sample Lobby Refresh | L-001 | Project kickoff and site review | 2 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 |  | Complete | Milestone
Sample Lobby Refresh | L-002 | Order lobby finish materials | 2 | 2026-01-06 | 2026-01-08 | 2026-01-06 | 2026-01-09 | 2 | Complete | Task
Sample Lobby Refresh | L-003 | Install temporary protection | 2 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 2026-01-09 | 3FS | Complete | Activity
Sample Lobby Refresh | L-004 | Remove existing finishes | 2 | 2026-01-12 | 2026-01-14 | 2026-01-14 | 2026-01-16 | 4FS+2d | Complete | Activity
Sample Lobby Refresh | L-SPEND-01 | Lobby budget check-in | 2 | 2026-01-12 | 2026-01-12 | 2026-01-13 | 2026-01-13 | 3FS | Updated | Spend
Sample Lobby Refresh | L-005 | Wall prep and paint | 2 | 2026-01-15 | 2026-01-20 | 2026-01-14 | 2026-01-20 | 5SS | In Progress | Activity
Sample Lobby Refresh | L-006 | Lighting refresh milestone | 2 | 2026-01-21 | 2026-01-21 | 2026-01-20 | 2026-01-20 | 3FS | Ready | Milestone
Sample Lobby Refresh | L-REPORT-01 | Weekly lobby status update | 2 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 2026-01-16 | 7FS | Sent | Reporting
Sample Lobby Refresh | L-007 | Remove old light fixtures | 2 | 2026-01-21 | 2026-01-22 | 2026-01-22 | 2026-01-23 | 4FS | In Progress | Activity
Sample Lobby Refresh | L-008 | Install new light fixtures | 2 | 2026-01-23 | 2026-01-27 | 2026-01-26 | 2026-01-28 | 10FS | Scheduled | Activity
Sample Lobby Refresh | L-009 | Final lobby walkthrough milestone | 2 | 2026-01-28 | 2026-01-28 | 2026-01-29 | 2026-01-29 | 8FS,11FS | Scheduled | Milestone
Sample Pool Repairs | P2 | Sample Pool Repairs | 1 | 2026-02-02 | 2026-02-23 | 2026-02-02 | 2026-02-24 |  | In Progress | Summary
Sample Pool Repairs | P-001 | Confirm repair scope | 2 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 |  | Complete | Milestone
Sample Pool Repairs | P-002 | Drain and clean pool | 2 | 2026-02-03 | 2026-02-04 | 2026-02-03 | 2026-02-05 | 14 | Complete | Activity
Sample Pool Repairs | P-003 | Surface inspection | 2 | 2026-02-05 | 2026-02-07 | 2026-02-06 | 2026-02-06 | 15FS | Complete | Task
Sample Pool Repairs | P-004 | Crack repair prep | 2 | 2026-02-09 | 2026-02-10 | 2026-02-09 | 2026-02-09 | 16FS+2d | Complete | Activity
Sample Pool Repairs | P-TILE | Tile repair package | 2 | 2026-02-11 | 2026-02-17 | 2026-02-10 | 2026-02-18 |  | In Progress | Summary
Sample Pool Repairs | P-005 | Remove damaged tile | 3 | 2026-02-11 | 2026-02-12 | 2026-02-10 | 2026-02-11 | 17FS | Complete | Activity
Sample Pool Repairs | P-006 | Install replacement tile | 3 | 2026-02-13 | 2026-02-17 | 2026-02-16 | 2026-02-18 | 19FS | In Progress | Activity
Sample Pool Repairs | P-007 | Optional owner walkthrough | 2 | 2026-02-18 | 2026-02-18 | 2026-02-19 | 2026-02-19 | 20FS | Optional | Milestone | No
Sample Pool Repairs | P-008 | Deck coating touch-up | 2 | 2026-02-18 | 2026-02-20 | 2026-02-17 | 2026-02-19 | 17SS | Scheduled | Activity
Sample Pool Repairs | P-SPEND-01 | Update pool budget tracker | 2 | 2026-02-19 | 2026-02-19 | 2026-02-20 | 2026-02-20 | 20FS | Updated | Spend
Sample Pool Repairs | P-009 | Final pool inspection milestone | 2 | 2026-02-23 | 2026-02-23 | 2026-02-24 | 2026-02-24 | 20FS,22FS | Scheduled | Milestone